## BurnDown
Project Title | KNR
Release # | 1.1 | [11 empty] | Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Sprint # | 1 | [11 empty] | Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
1 | Create Repository for the group |  | Kurt | 1 | [7 empty] | 1 | Step 4 | Break the User Story into a series of step by step development tasks in Column D
2 | Create MVC Project Files for login/registration modules |  | Kurt | 1 | [7 empty] | 1 | Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
3 | Create the spreadsheets for the scrum artifacts |  | Kurt | 1 | [7 empty] | 1 | Step 6 | Assign the User Story to a single Team Member in Column E
4 | Contribute to sprint backlog |  | Nick | 1 | [8 empty] | Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
5 | Contribute to sprint product log |  | Nick | 1 | [8 empty] | Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
[13 empty] | Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time

## Product Log
Project Title | KNR
Release # | 1.1
Sprint # | 1
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
| 1 | login page |  | login form with password encryption | user is secure | high
| 2 | registration page |  | registration form | new users | high
| 3 | gameboard |  | programming for gameboard with multiple layouts | the user can have different options of play | high
| 4 | user database table |  | store all user data | keep track of users | high
| 5 | leaderboard function |  | algorithm to determine the leaders amongst those in the user DB | leaders can be ordered | med

## BackLog
Project Title | KNR
Release # | 1.1
Sprint # | 1
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
| 1 | Login | user | login page for game | give users a more personal experience | high
| 2 | registration | user | allow new players to register | new players can register to play the game | high
| 3 | game board | admin | layout of gameboard | to have the gameboard strategicaly mapped out for gameplay | high
| 4 | game status | users | allow game progress to be saved | users can pick up the game where they left of last | med
| 5 | controls | admin | functions for certain game play moves | certain spaces landed on have either benifits or consiquences | med
| 6 | visual | users | overall appearance of gameboard | to have a visually pleasing gamebaord | med
| 7 | leaderboard | users | shows rank of users games | users can see where they sit amongst others users of the game | low