## BurnDown
Project Title | KNR
Release # | 1.2 | [11 empty] | Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Sprint # | 2 | [11 empty] | Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
User Story ID | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 4 | Day 5 | Day 6 | Day 7 | Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
1 | Create sprint backlog |  | Nick | 1 | [7 empty] | 1 | Step 4 | Break the User Story into a series of step by step development tasks in Column D
2 | Create sprint product log |  | Nick | 1 | [7 empty] | 1 | Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
3 | Create burndown |  | Nick | 1 | [7 empty] | 1 | Step 6 | Assign the User Story to a single Team Member in Column E
4 | Flow chart |  | Ray | 1 | [8 empty] | Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
5 | Login Page |  | Team Members | 1 | [8 empty] | Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
6 | Registration Page |  | Kurt | [9 empty] | Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time
7 | Design report |  | Team Members

## Product Log
Project Title | KNR
Release # | 1.2
Sprint # | 2
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
1 | 1 | login view page |  | login form | user login | high
2 | 2 | registration view page |  | registration form | new users register | high
3 | 3 | user database table |  | store all user data | keep track of users | high
4 | 4 | login Controller |  | login controller/ validation | login code | high
5 | 5 | Registration Controller |  | registration controller/ validation | registration code | high
6 | 6 | error/success views |  | validations views for login/registration | view pages | high

## BackLog
Project Title | KNR
Release # | 1.2
Sprint # | 2
User Stories
ID | Feature | User Story | As a(n) <actor> | I would like to <description> | So that <outcome> | Priority | Sign-off Date | Modification Date
1 | 1 | Login | user | login page for game | give users a more personal experience | high
2 | 2 | registration | user | allow new players to register | new players can register to play the game | high
3 | 3 | controls | admin | control the data doe registered users | users may still be able to get access to data if password is lost | med
4 | 4 | visual | users | overall appearance of the view pages | to have a visually pleasing login/registration views | med
| 5 | storage | admin | data base with all game/user data | to be able to store and locate user data | high